## Background
Risk Assessment Model® (RAM®)
Project Name | Project Reference Number |  | Prepared By (print) | Preparer's Initials
Customer | Contact |  | Contact's Phone # | Date Prepared
Background
The ESI Risk Assessment Model® (RAM®) is a valuable tool for use in the early life-cycle phases of a project or
contracting opportunity. Its primary purpose is to assist management and decision makers with project selection
or bid/no-bid decisions. The RAM® model has been developed by ESI based on studies of actual projects and
contracts and consultation with decision makers. These studies have shown repeatedly that project selection
and bid/no-bid decisions are made with considerations for both the potential threats and the potential opportunities.
The RAM® questions have been found in these studies to be the critical questions upon which decisions are
made. However, because every company, industry, and culture is different, it is recommended that the tool be
customized over time in order to more closely represent your company, data, strategy, market segment, and
organizational risk tolerances. Our intent is to provide the framework for your use.
Use
The ESI RAM® tool is easy to use. Appropriate answers are determined for the probability and impact questions
presented for threat and opportunity. Scores are totalled and plotted on the decision scale at the end of the tool.
Recommendations then are read from the decision scale on whether this is a project that should be invested in,
avoided, or studied further.
Because probability and impact essentially are subjective in nature (different people have different opinions), it is
recommended that at least four to six key project team members be assembled for an “assessment” meeting to
determine the answers to the probability and impact questions. A facilitator who could lead the meeting should
be identified. The facilitator then should walk the group through each of the RAM® questions. After the
questions are read aloud, the facilitator should lead the group to a consensus answer for the probability and
impact for each question. The appropriate box is selected on the tool for each of the probability and impact
questions. The threat exposure (TE) and the opportunity exposure (OE) are obtained for each question by
multiplying the quantity of the selected probability by the quantity of the selected impact. After all 40 questions
have been answered, a total threat exposure score is obtained by adding up the TE for the 20 risk assessment
questions. Similarly, a total opportunity exposure score is obtained by adding up the OE for the 20 opportunity
assessment questions.
These two quantities then are plotted on the ESI decision scale, which is found on the last page of this document.
The total threat exposure score is marked on the threat scale, and the total opportunity exposure score is located
on the opportunity scale. A line is drawn between these two points. The recommended decision is read off the
decision scale at the point where the line drawn crosses the decision scale.
Interpretation
Projects are good investments when threats are low and opportunities are high. Projects are not good investments
when threats are high and opportunities are low. Other combinations of threat and opportunity require additional
scrutiny and require a closer examination of project particulars. As with any decision, many variables must be
considered. The elements of the ESI RAM® have been selected as they represent the most significant variables
typically involved in the project selection decision.
Organizational Considerations
As mentioned above, every company organization is different, with differing business needs. As such, it is highly
recommended that the ESI RAM® tool be customized for more effective application in your company. Our
studies have shown that these are the right questions; however, some adjustment, weighting, or further definition
may be required to more closely model your company’s business goals and focus. The following are areas that
your company should consider for customization:
n Probability scale
n Impact scale
n Weighting factors
The goal of these customizations is to have the tool more closely model the decisions that your company’s
executives would make.
Probability Scale
Because every company organization is different, give thought to possibly modifying the probability scale
presented with each of the questions contained in the RAM® tool.
The tool is designed with the following criteria for the Probability of Occurrence questions:
|  | Question | Probability of Occurrence
|  | 1 | = 1 to 10%
|  | 2 | = 11 to 20%
|  | 3 | = 21 to 30%
|  | 4 | = 31 to 40%
|  | 5 | = 41 to 50%
|  | 6 | = 51 to 60%
|  | 7 | = 61 to 70%
|  | 8 | = 71 to 80%
|  | 9 | = 81 to 90%
|  | 10 | = 91 to 100%
Impact Scale
The impact scale is, again, a subjective measure. To ensure consistency of use, the organization should consider
providing a definition of each response to tool users. For example, the impact scale could be customized into
percentages.
Weighting Factors
If deemed necessary, weighting factors could be added to adjust the importance of any of the 40 questions, based
on current company priorities and focus items. The weighting factors would be added as multipliers for the
corresponding questions. Once the weighting factors are added, the basic process for use of the tool would
remain the same.

## Threat Analysis
Threat Analysis
Customer Threats
|  | Probability of Occurrence |  |  |  | Impact of Occurrence |  |  | TE
1. | Customer Relationship | Based on the proposal team's assessment of our company's current or prior relationship with this customer, what is the probability that we could experience cost, schedule, or performance problems in our execution of this contract? |  |  | x | If problems do occur as a result of our current or prior relationship with this customer, what could be the extent of the impact on the project success criteria for this project? |  | = | 0
|  | Virtually Improbable |  | Virtually Certain |  | Very Little Extent | Very Great Extent
|  | 1 2 3 4 5 6 7 8 9 10 |  |  |  | 1 2 3 4 5 6 7 8 9 10
2. | Customer Readiness | Based on the proposal team’s assessment of the customer’s readiness to undertake this project, what is the probability that we could experience cost, schedule, or performance problems in our execution of this contract? |  |  | x | If problems do occur as a result of the customer’s readiness to undertake this project, what could be the extent of the impact on the project success criteria for this project? |  | = | 0
|  | Virtually Improbable |  | Virtually Certain |  | Very Little Extent | Very Great Extent
|  | 1 2 3 4 5 6 7 8 9 10 |  |  |  | 1 2 3 4 5 6 7 8 9 10
3. | Customer Commitment | Based on the proposal team’s assessment of the customer’s level of commitment of resources and budget to this project, what is the probability that we could experience cost, schedule, or performance problems in our execution of this contract? |  |  | x | If problems do occur as a result of the customer’s commitment of resources and budget to this project, what could be the extent of the impact on the project success criteria for this project? |  | = | 0
|  | Virtually Improbable |  | Virtually Certain |  | Very Little Extent | Very Great Extent
|  | 1 2 3 4 5 6 7 8 9 10 |  |  |  | 1 2 3 4 5 6 7 8 9 10
Contract Threats
|  | Probability of Occurrence |  |  |  | Impact of Occurrence |  |  | TE
4. | Contract Document | Based on the proposal team’s assessment of customer-driven changes to our company’s standard contract, what is the probability that we could experience cost, schedule, or performance problems in our execution of this contract? |  |  | x | If problems do occur as a result of these customer-driven contract changes, what could be the extent of the impact on project success criteria for this project? |  | = | 0
|  | Virtually Improbable |  | Virtually Certain |  | Very Little Extent | Very Great Extent
|  | 1 2 3 4 5 6 7 8 9 10 |  |  |  | 1 2 3 4 5 6 7 8 9 10
5. | Contract Type | Based on the proposal team’s assessment of the contract type for this project (fixed-price, T&M, CPIF, and so on), what is the probability that we could experience cost, schedule, or performance problems in our execution of this contract? |  |  | x | If problems do occur as a result of the contract type for this project, what could be the extent of the impact on the project success criteria for this project? |  | = | 0
|  | Virtually Improbable |  | Virtually Certain |  | Very Little Extent | Very Great Extent
|  | 1 2 3 4 5 6 7 8 9 10 |  |  |  | 1 2 3 4 5 6 7 8 9 10
6. | Contract Performance Guarantees | Based on the proposal team’s assessment of the extent of customer-driven performance guarantees, what is the probability that we could experience cost, schedule, or performance problems in our execution of this contract? |  |  | x | If problems do occur as a result of the customer-driven performance guarantees, what could be the extent of the impact on the project success criteria for this project? |  | = | 0
|  | Virtually Improbable |  | Virtually Certain |  | Very Little Extent | Very Great Extent
|  | 1 2 3 4 5 6 7 8 9 10 |  |  |  | 1 2 3 4 5 6 7 8 9 10
Project Schedule Threats
|  | Probability of Occurrence |  |  |  | Impact of Occurrence |  |  | TE
7. | Response Time Frame | Based on the proposal team’s assessment of the time that the proposal team has had to respond to and submit this proposal, what is the probability that we could experience cost, schedule, or performance problems in our execution of this contract? |  |  | x | If problems do occur as a result of these customer-driven contract changes, what could be the extent of the impact on project success criteria for this project? |  | = | 0
|  | Virtually Improbable |  | Virtually Certain |  | Very Little Extent | Very Great Extent
|  | 1 2 3 4 5 6 7 8 9 10 |  |  |  | 1 2 3 4 5 6 7 8 9 10
8. | Project Milestone Timetable | Based on the proposal team’s assessment of our company’s ability to meet key project milestone dates, what is the probability that we could experience cost, schedule, or performance problems in our execution of this contract? |  |  | x | If problems do occur as a result of our company’s ability to meet these key project milestone dates, what could be the extent of the impact on project success criteria for this project? |  | = | 0
|  | Virtually Improbable |  | Virtually Certain |  | Very Little Extent | Very Great Extent
|  | 1 2 3 4 5 6 7 8 9 10 |  |  |  | 1 2 3 4 5 6 7 8 9 10
9. | Project Duration | Based on the proposal team’s assessment of the overall project duration relative to the scope of the project, what is the probability that we could experience cost, schedule, or performance problems in our execution of this contract? |  |  | x | If problems do occur as a result of the overall duration of this project relative to the scope, what could be the extent of the impact on the project success criteria for this project? |  | = | 0
|  | Virtually Improbable |  | Virtually Certain |  | Very Little Extent | Very Great Extent
|  | 1 2 3 4 5 6 7 8 9 10 |  |  |  | 1 2 3 4 5 6 7 8 9 10
Project Complexity Threats
|  | Probability of Occurrence |  |  |  | Impact of Occurrence |  |  | TE
10. | Project Complexity | Based on the proposal team’s assessment of the complexity of the project, what is the probability that we could experience cost, schedule, or performance problems in our execution of this contract? |  |  | x | If problems do occur as a result of project complexity, what could be the extent of the impact on project success criteria for this project? |  | = | 0
|  | Virtually Improbable |  | Virtually Certain |  | Very Little Extent | Very Great Extent
|  | 1 2 3 4 5 6 7 8 9 10 |  |  |  | 1 2 3 4 5 6 7 8 9 10
11. | Project Definition | Based on the proposal team’s assessment of the adequacy of our company’s involvement in the definition of the project, what is the probability that we will experience cost, schedule, or performance problems in our execution of this contract? |  |  | x | If problems do occur as a result of the adequacy of our involvement in the definition of the project, what could be the extent of the impact on project success criteria for this project? |  | = | 0
|  | Virtually Improbable |  | Virtually Certain |  | Very Little Extent | Very Great Extent
|  | 1 2 3 4 5 6 7 8 9 10 |  |  |  | 1 2 3 4 5 6 7 8 9 10
12. | Changing Requirements | Based on the proposal team’s assessment of the potential for changes in project requirements, what is the probability that we will experience cost, schedule, or performance problems in our execution of this contract? |  |  | x | If problems do occur as a result of changes in project requirements, what could be the extent of the impact on project success criteria for this project? |  | = | 0
|  | Virtually Improbable |  | Virtually Certain |  | Very Little Extent | Very Great Extent
|  | 1 2 3 4 5 6 7 8 9 10 |  |  |  | 1 2 3 4 5 6 7 8 9 10
13. | Similar Experience | Based on the proposal team’s assessment of the prior similar experience of the potential project team, what is the probability that we will experience cost, schedule, or performance problems in our execution of this contract? |  |  | x | If problems do occur as a result of the assigned project team’s prior similar experience, what could be the extent of the impact on project success criteria for this project? |  | = | 0
|  | Virtually Improbable |  | Virtually Certain |  | Very Little Extent | Very Great Extent
|  | 1 2 3 4 5 6 7 8 9 10 |  |  |  | 1 2 3 4 5 6 7 8 9 10
14. | Use of Nonmature Products | Based on the proposal team’s assessment of the extent to which nonmature products will be used in the project, what is the probability that we will experience cost, schedule, or performance problems in our execution of this contract? |  |  | x | If problems do occur as a result of the extent to which nonmature products will be used, what could be the extent of the impact on project success criteria for this project? |  | = | 0
|  | Virtually Improbable |  | Virtually Certain |  | Very Little Extent | Very Great Extent
|  | 1 2 3 4 5 6 7 8 9 10 |  |  |  | 1 2 3 4 5 6 7 8 9 10
Project Environment Threats
|  | Probability of Occurrence |  |  |  | Impact of Occurrence |  |  | TE
15. | Number of Suppliers or Contractors | Based on the proposal team’s assessment of the number of suppliers and contractors that will be used on the project, what is the probability that we will experience cost, schedule, or performance problems in our execution of this contract? |  |  | x | If problems do occur as a result of the number of suppliers and contractors that will be used on the project, what could be the extent of the impact on project success criteria for this project? |  | = | 0
|  | Virtually Improbable |  | Virtually Certain |  | Very Little Extent | Very Great Extent
|  | 1 2 3 4 5 6 7 8 9 10 |  |  |  | 1 2 3 4 5 6 7 8 9 10
16. | Geographic Distribution | Based on the proposal team’s assessment of the geographic distribution of the project work and the associated logistics, what is the probability that we will experience cost, schedule, or performance problems in our execution of this contract? |  |  | x | If problems do occur as a result of the geographic distribution of the project work and the associated logistics, what could be the extent of the impact on project success criteria for this project? |  | = | 0
|  | Virtually Improbable |  | Virtually Certain |  | Very Little Extent | Very Great Extent
|  | 1 2 3 4 5 6 7 8 9 10 |  |  |  | 1 2 3 4 5 6 7 8 9 10
17. | Resource Availability | Based on the proposal team’s assessment of the required resources being available as planned to perform project work scope, what is the probability that we will experience cost, schedule, or performance problems in our execution of this contract? |  |  | x | If problems do occur as a result of resource availability, what could be the extent of the impact on project success criteria for this project? |  | = | 0
|  | Virtually Improbable |  | Virtually Certain |  | Very Little Extent | Very Great Extent
|  | 1 2 3 4 5 6 7 8 9 10 |  |  |  | 1 2 3 4 5 6 7 8 9 10
18. | Specialized Skills | Based on the proposal team’s assessment of the need and availability of specialized skills to perform the project work, what is the probability that we will experience cost, schedule, or performance problems in our execution of this contract? |  |  | x | If problems do occur as a result of the need and availability of specialized skills, what could be the extent of the impact on project success criteria for this project? |  | = | 0
|  | Virtually Improbable |  | Virtually Certain |  | Very Little Extent | Very Great Extent
|  | 1 2 3 4 5 6 7 8 9 10 |  |  |  | 1 2 3 4 5 6 7 8 9 10
Project Management Threats
|  | Probability of Occurrence |  |  |  | Impact of Occurrence |  |  | TE
19. | Project Authority | Based on the proposal team’s assessment of the adequacy of the project manager’s delegated authority level for the project, what is the probability that we will experience cost, schedule, or performance problems in our execution of this contract? |  |  | x | If problems do occur as a result of the adequacy of the project manager’s delegated authority, what could be the extent of the impact on project success criteria for this project? |  | = | 0
|  | Virtually Improbable |  | Virtually Certain |  | Very Little Extent | Very Great Extent
|  | 1 2 3 4 5 6 7 8 9 10 |  |  |  | 1 2 3 4 5 6 7 8 9 10
20. | Project Manager’s Risk Assessment | Based solely on the project manager’s assessment, what is the probability that we will experience cost, schedule, or performance problems in our execution of this contract? |  |  | x | Based solely on the project manager’s assessment of the probability of problems occurring, if problems do occur, what could be the extent of the impact on project success criteria for this project? |  | = | 0
|  | Virtually Improbable |  | Virtually Certain |  | Very Little Extent | Very Great Extent
|  | 1 2 3 4 5 6 7 8 9 10 |  |  |  | 1 2 3 4 5 6 7 8 9 10
|  |  | Total Threat Score (sum of 1 through 20) = | [5 empty] | 0
Group Box 1292
Group Box 1303
Group Box 1314
Group Box 1325
Group Box 1336
Group Box 1347
Group Box 1358
Group Box 1369
Group Box 1380
Group Box 1391
Group Box 1402
Group Box 1413
Group Box 1424
Group Box 1435
Group Box 1446
Group Box 1457
Group Box 1468
Group Box 1479
Group Box 1490
Group Box 1501
Group Box 1512
Group Box 1523
Group Box 1534
Group Box 1545
Group Box 1556
Group Box 1567
Group Box 1578
Group Box 1589
Group Box 1600
Group Box 1611
Group Box 1622
Group Box 1633
Group Box 1644
Group Box 1655
Group Box 1666
Group Box 1677
Group Box 1688
Group Box 1699
Group Box 1710
Group Box 1721

## Opportunity Analysis
Opportunity Analysis
Strategic Business Opportunities
|  | Probability of Occurrence |  |  |  | Impact of Occurrence |  |  | OE
1. | Promotes Company’s Strategic Direction | Based on the project team’s assessment, what is the probability that this contract, when finally signed, will promote and be consistent with the major components of the company’s strategic direction? |  |  | x | What is the extent to which this project is consistent with the strategic direction of the company? |  | = | 0
|  | Virtually Improbable |  | Virtually Certain |  | Very Little Extent | Very Great Extent
|  | 1 2 3 4 5 6 7 8 9 10 |  |  |  | 1 2 3 4 5 6 7 8 9 10
2. | Market Share Improvement | Based on the proposal team’s assessment, what is the probability that winning this project and its successful completion could lead to an improvement in the company’s market share over the next 12 months? |  |  | x | What is the extent to which an improvement in market share could be realized in the next 12 months if the project is successfully completed? |  | = | 0
|  | Virtually Improbable |  | Virtually Certain |  | Very Little Extent | Very Great Extent
|  | 1 2 3 4 5 6 7 8 9 10 |  |  |  | 1 2 3 4 5 6 7 8 9 10
Resource and Skill Opportunities
|  | Probability of Occurrence |  |  |  | Impact of Occurrence |  |  | OE
3. | Resource Use | Based on the proposal team’s assessment, what is the probability that winning and executing this project could allow our company to use resources that are currently underutilized in the company? |  |  | x | What is the extent to which these underutilized resources could be converted to billable resources in the next 12 months? |  | = | 0
|  | Virtually Improbable |  | Virtually Certain |  | Very Little Extent | Very Great Extent
|  | 1 2 3 4 5 6 7 8 9 10 |  |  |  | 1 2 3 4 5 6 7 8 9 10
4. | New Skill Development | Based on the proposal team’s assessment, what is the probability that winning and performing this project could allow our company to develop new skills that might lead to eventual increases in revenue and profit in the next 24 months? |  |  | x | What is the extent to which these new skills developed by performing this project could contribute to increases in revenue and profit in the next 24 months? |  | = | 0
|  | Virtually Improbable |  | Virtually Certain |  | Very Little Extent | Very Great Extent
|  | 1 2 3 4 5 6 7 8 9 10 |  |  |  | 1 2 3 4 5 6 7 8 9 10
5. | Provides Added Experience | Based on the proposal team’s assessment, what is the probability that winning and executing this project could allow our company to expand our current skill base in this area? |  |  | x | What is the extent to which this expanded skill base, obtained by performing this project, could result in additional revenue and profit in the next 12 months? |  | = | 0
|  | Virtually Improbable |  | Virtually Certain |  | Very Little Extent | Very Great Extent
|  | 1 2 3 4 5 6 7 8 9 10 |  |  |  | 1 2 3 4 5 6 7 8 9 10
New Business Marketing Opportunities
|  | Probability of Occurrence |  |  |  | Impact of Occurrence |  |  | OE
6. | Customer Reference | Based on the proposal team’s assessment, what is the probability, if the project is successfully completed, that this customer would agree to serve as a reference site? |  |  | x | What is the extent to which our company could benefit by this specific customer being a reference site if the project is successfully completed? |  | = | 0
|  | Virtually Improbable |  | Virtually Certain |  | Very Little Extent | Very Great Extent
|  | 1 2 3 4 5 6 7 8 9 10 |  |  |  | 1 2 3 4 5 6 7 8 9 10
7. | Future Potential | Based on the proposal team’s assessment, what is the probability that successful completion of this project will lead to additional business with this customer? |  |  | x | What is the extent to which additional business with this customer may be realized with successful completion of this project? |  | = | 0
|  | Virtually Improbable |  | Virtually Certain |  | Very Little Extent | Very Great Extent
|  | 1 2 3 4 5 6 7 8 9 10 |  |  |  | 1 2 3 4 5 6 7 8 9 10
8. | Media Coverage | Based on the proposal team’s assessment, what is the probability that the winning of this project and its successful completion will provide the opportunity for positive media coverage? |  |  | x | What is the extent to which this media coverage could assist with winning additional business in the next 12 months if the project is successfully completed? |  | = | 0
|  | Virtually Improbable |  | Virtually Certain |  | Very Little Extent | Very Great Extent
|  | 1 2 3 4 5 6 7 8 9 10 |  |  |  | 1 2 3 4 5 6 7 8 9 10
9. | Social Influence | Based on the proposal team’s assessment, what is the probability that successful completion of this project could influence other business leaders to do business with our company in the future? |  |  | x | What is the extent to which other business leaders could be influenced to do business with our company with successful completion of this project? |  | = | 0
|  | Virtually Improbable |  | Virtually Certain |  | Very Little Extent | Very Great Extent
|  | 1 2 3 4 5 6 7 8 9 10 |  |  |  | 1 2 3 4 5 6 7 8 9 10
Project Financial Opportunities
|  | Probability of Occurrence |  |  |  | Impact of Occurrence |  |  | OE
10. | Revenue Objectives | Based on the proposal team’s assessment, what is the probability that the revenue objectives will be met or exceeded on this project? |  |  | x | What is the extent to which this project will meet or exceed revenue objectives for this project? |  | = | 0
|  | Virtually Improbable |  | Virtually Certain |  | Very Little Extent | Very Great Extent
|  | 1 2 3 4 5 6 7 8 9 10 |  |  |  | 1 2 3 4 5 6 7 8 9 10
|  | Probability of Occurrence |  |  |  | Impact of Occurrence |  |  | OE
11. | Time Frame | Based on the proposal team’s assessment, what is the probability that significant revenue from this project will be earned within the next 12 months? |  |  | x | What is the extent to which this project will earn significant revenue for the company in the next 12 months? |  | = | 0
|  | Virtually Improbable |  | Virtually Certain |  | Very Little Extent | Very Great Extent
|  | 1 2 3 4 5 6 7 8 9 10 |  |  |  | 1 2 3 4 5 6 7 8 9 10
12. | Annual Cash Flow | Based on the proposal team’s assessment, what is the probability that the project will have a positive cash flow during the next 12 months of operation? |  |  | x | What is the extent to which this project will produce a positive cash flow in the next 12 months? |  | = | 0
|  | Virtually Improbable |  | Virtually Certain |  | Very Little Extent | Very Great Extent
|  | 1 2 3 4 5 6 7 8 9 10 |  |  |  | 1 2 3 4 5 6 7 8 9 10
13. | Margin Goals | Based on the proposal team’s assessment, what is the probability that the margin goals for this project will be met or exceeded over the lifetime of the project? |  |  | x | What is the extent to which margin goals for this project will be met or exceeded over the lifetime of the project? |  | = | 0
|  | Virtually Improbable |  | Virtually Certain |  | Very Little Extent | Very Great Extent
|  | 1 2 3 4 5 6 7 8 9 10 |  |  |  | 1 2 3 4 5 6 7 8 9 10
14. | Net Present Value | Based on the proposal team’s assessment, what is the probability that the project will meet or exceed the net present value objectives of the project over the lifetime of the project? |  |  | x | What is the extent to which the project will meet or exceed the net present value objectives of the project over the lifetime of the project? |  | = | 0
|  | Virtually Improbable |  | Virtually Certain |  | Very Little Extent | Very Great Extent
|  | 1 2 3 4 5 6 7 8 9 10 |  |  |  | 1 2 3 4 5 6 7 8 9 10
15. | Presale Cost | Based on the proposal team’s assessment, what is the probability that the presale costs (costs incurred before contract signing) will be small relative to the overall revenue and profit of the project? |  |  | x | What is the extent to which presale costs on this project could be small relative to the overall revenue and profit of the project? |  | = | 0
|  | Virtually Improbable |  | Virtually Certain |  | Very Little Extent | Very Great Extent
|  | 1 2 3 4 5 6 7 8 9 10 |  |  |  | 1 2 3 4 5 6 7 8 9 10
Project Scope Opportunities
|  | Probability of Occurrence |  |  |  | Impact of Occurrence |  |  | OE
16. | Service Content | Based on the proposal team’s assessment, what is the probability that our company could expand the service content of this contract over the next 12 months? |  |  | x | What is the extent to which service content of this contract could be expanded in the next 12 months? |  | = | 0
|  | Virtually Improbable |  | Virtually Certain |  | Very Little Extent | Very Great Extent
|  | 1 2 3 4 5 6 7 8 9 10 |  |  |  | 1 2 3 4 5 6 7 8 9 10
17. | Product Content | Based on the proposal team’s assessment, what is the probability that our company could expand the product content of this contract over the next 12 months? |  |  | x | What is the extent to which product content of this contract could be expanded in the next 12 months? |  | = | 0
|  | Virtually Improbable |  | Virtually Certain |  | Very Little Extent | Very Great Extent
|  | 1 2 3 4 5 6 7 8 9 10 |  |  |  | 1 2 3 4 5 6 7 8 9 10
Overall Opportunity Assessments
|  | Probability of Occurrence |  |  |  | Impact of Occurrence |  |  | OE
18. | Customer Preference | Based on the proposal team’s assessment, what is the probability that the customer already has a preference or predisposition to do business with our company? |  |  | x | What is the extent to which the customer prefers to do business with our company versus the competition? |  | = | 0
|  | Virtually Improbable |  | Virtually Certain |  | Very Little Extent | Very Great Extent
|  | 1 2 3 4 5 6 7 8 9 10 |  |  |  | 1 2 3 4 5 6 7 8 9 10
19. | Marketing Assessment of Opportunity | Based on marketing’s assessment, what is the probability that winning and successfully completing this project could represent a very significant opportunity to our company over the long haul? |  |  | x | Based on marketing’s assessment, how significant an opportunity does this project represent to our company over the long haul? |  | = | 0
|  | Virtually Improbable |  | Virtually Certain |  | Very Little Extent | Very Great Extent
|  | 1 2 3 4 5 6 7 8 9 10 |  |  |  | 1 2 3 4 5 6 7 8 9 10
20. | Project Manager’s Assessment of Opportunity | Based on the project manager’s assessment, what is the probability that winning and successfully completing this project could represent a very significant opportunity to our company over the long haul? |  |  | x | Based on the project manager’s assessment, how significant an opportunity does this project represent to our company over the long haul? |  | = | 0
|  | Virtually Improbable |  | Virtually Certain |  | Very Little Extent | Very Great Extent
|  | 1 2 3 4 5 6 7 8 9 10 |  |  |  | 1 2 3 4 5 6 7 8 9 10
|  |  | Total Opportunity Score (sum of 1 through 20) = | [5 empty] | 0
0
Group Box 1343
Group Box 1354
Group Box 1365
Group Box 1376
Group Box 1387
Group Box 1398
Group Box 1409
Group Box 1420
Group Box 1431
Group Box 1442
Group Box 1453
Group Box 1464
Group Box 1475
Group Box 1486
Group Box 1497
Group Box 1508
Group Box 1519
Group Box 1530
Group Box 1541
Group Box 1552
Group Box 1563
Group Box 1574
Group Box 1585
Group Box 1596
Group Box 1607
Group Box 1618
Group Box 1629
Group Box 1640
Group Box 1651
Group Box 1662
Group Box 1673
Group Box 1684
Group Box 1695
Group Box 1706
Group Box 1717
Group Box 1728
Group Box 1739
Group Box 1750
Group Box 1761
Group Box 1772

## Threat-Opportunity Dec. Scale
Threat-Opportunity Decision Scale